RISK ANALYSIS AND CONTINGENCY PLAN

The project has been funded with support from the European Commission - Erasmus+ Programme. This publication reflects the views only of the author and the Commission cannot be held responsible for any use which may be made of the information contained therein.

Project number: 2021-1-IT01-KA220-VET-000034771

# Project title: STARLIGHT – Skills for Tourism And Recognition of the importance of dark skies

# Reference number: 2021-1-IT01-KA220-VET-000034771

# Period of implementation: 01/02/2022 – 31/01/2025

# CONTINGENCY PLAN FOR THE STARLIGHT PROJECT

This is a Contingency Plan regarding the STARLIGHT project, built to highlight potential risks that might happen during its development and the proposed actions to be implemented in order not to jeopardize it.

The analysis, if relevant, will be updated during project implementation.

The identified risks are mainly linked to these 5 topics:

- PROJECT PLAN;

- PARTNERSHIP AND COOPERATION;

- PROJECT MANAGEMENT /IMPLEMENTATION;

- STAKEHOLDERS;

- EXTERNAL ENVIRONMENT.

| RISK / TRIGGERING EVENT | PROBABILITY OF OCCURRENCE | POSSIBLE CONSEQUENCE | PREVENTIVE / CORRECTIVE ACTION |
| --- | --- | --- | --- |
| PROJECT PLAN |  |  |  |
| Impossibility to respect the project plan | Low | Occasionally it may happen, causing a slight slippage of internal targets and tasks: project timing is mainly affected | The timetable must be kept constantly under control as many actions depend on successful implementation of others. Meetings to be organised, involving a limited number of partners to solve problems and doubts related to project management and activities implementation. |
| PARTNERSHIP AND COOPERATION |  |  |  |
| Risk of changes at the decisional level | Low | Possible slippage in achievements and slight reduction of result effectiveness | Keeping a constant communication flow among partners and apply PSC rules. |
| Misunderstanding among partners | Low | Possible slippage in achievements and slight reduction of result effectiveness | Apply PSC rules in due time to solve misunderstandings and organize restricted meetings. |
| PROJECT MANAGEMENT/ IMPLEMENTATION |  |  |  |
| Risks referred to staff involved | Very low | Slippage in timetable and ineffectiveness of project results | Keeping a constant communication flow and the timetable under control |
| Difficulties in the recruitment of young professionals willing to participate to STARLIGHT activity | Medium | Slippage in timetable and ineffectiveness of project results | Involve stakeholders and keep them informed and engaged in project activities dissemination; Enlarge partners network; Improve communication and dissemination activities. Start recruitment at early stage of project implementation to perform a correct and high-quality selection. |
| Unsuccessful dissemination activities | Low | Not reaching a minimum number of participants; Low interest on the project and in the professional competences it develops. | Verify stakeholders addressed and eventually enlarge the network; Find social media pages, websites, etc. that might be interested in supporting project activities dissemination |
| STAKEHOLDERS |  |  |  |
| Low interest | Medium | Reduction of dissemination activities and project sustainability, especially after its closure | Efficient communication activity and stakeholders engagement |
| “Adverse” stakeholders | Low | Reduction of dissemination activities and project sustainability, especially after its closure |  |
| EXTERNAL ENVIRONMENT |  |  |  |
| Risks connected to external environments, like pandemic, economic recession, etc. | Medium | Impact on project implementation and partners finances (e.g. requirement of additional funds) | Constant communication flow, PSC establishment to define a shared strategy |