Planned activities and time frame

| Task | Responsible | Time frame/Deadline |
| --- | --- | --- |
| Fill out Doodle for next Partner Meeting | All partner | asap |
| Fill out Evaluation Sheet for Kick-Off Meeting | All partner | asap |
| Template Toolkit structure | INAF | 15/06/2022 |
| Fill out Doodle for Communication Meeting | Communication Manager | 15/06/2022 |
| Send partner description and organization logo, prepare a page dedicated to the project on the partner webpage, become admin for Facebook and LinkedIn | Communication Manager | June 2022 |
| Sharing final Project-Logo | GAL EVV | 17/06/2022 |
| Communication meeting | Communication Manager | End of June/Beginning of July |
| Web structure ready | Communication Manager+ all partner | 31/07/2022 |
| Stakeholder Mapping | All partner | End of August |
| First reporting Budget Progress Report, Project Results advancement report, Timesheets | All partner | Mid of September |
| Toolkit draft pages | All partner | 15/09/2022 |
| Next Partner Meeting | INAF+All partner | 15/09-15/10/2022 |
| Toolkit web implementation | Communication Manager | 15/10/2022 |
| Validation and proof reading | NBDN and RRANG | 15/11/2022 |
| Draft Toolkit ready | All partner | 15/11/2022 |
| First Webinar | (RRANG) | April 2023 |
| First Summer School | (NBDN) | Nov/Dec 2023 |